## CONTACTS BILLING
KEY CONTACTS
POSITION / ROLL | NAME | COMPANY | MOBILE | EMAIL
Sponsor & Festival Lead | Tyler Hutchinson | Tourism WA
Venue & event promoter | Greg Sleigh Gemma Felton Wendy Quinn Bec Coxall | Optus Stadium
Coordination & programming | Frank Miranda | Perth Italian Festival
Consultation & community engagement | Sal Vallelonga | Sal Vallelonga
Event facilitation & project working group | Jo Metcalf Carol Hodgen | CITS
CaLD participation & engagement | Kate Rowlands | Office of Multicultural Interests
Festival operations & logistics | Kyle Bailey | Kyron Events
Power / Electricians | Sheldon Lobel | Lobel
#VALUE!
BILLING DETAILS
Name:
Company:
Postal:
Address:
ABN:

## CHECKLIST
OPERATIONS / LOGISTICS / INFRASTRUCTURE CHECKLIST
ITEM (EXPENSES) | DETAILS | SUPPLIER | RESPONSIBLE | RFQ SENT | BOOKED | PAID
PORTABLES (BUILDINGS)
20ft Site Office | KYRON OFFICE | KYRON |  | FALSE
20ft Bar container | (TBC) | CR |  | FALSE
Ticket box (20ft) | (TBC) | CR |  | FALSE
FALSE
FALSE
FALSE
TOILETS
Portaloos (see toilet calculator) | 30x Portaloos | PERTH HIRE SHOP |  | FALSE
BOH Portaloos | 2x | PERTH HIRE SHOP |  | FALSE
ADA Portaloos | 2x | PERTH HIRE SHOP |  | FALSE
FALSE
FALSE
FALSE
OPERATIONS & LOGISTICS
Event Application | REQUIRED? | KYRON |  | FALSE
Transport Schedule | TO DO | KYRON |  | FALSE
Furniture Distro |  | KYRON |  | FALSE
Production Schedule | TO DO | KYRON |  | FALSE
Build Schedule | TO DO | KYRON |  | FALSE
Event Management Plan | TO DO | KYRON |  | FALSE
Risk Management Plan | TO DO | KYRON |  | FALSE
Key Contacts List | TO DO | KYRON |  | FALSE
Site Map | REV 2 - Draft completed | KYRON |  | FALSE
Liquor Licence | VL & MIZZICA | KYRON |  | FALSE
Electrical Form 5 | Electricians to provide | KYRON |  | FALSE
Major Structures List / Engineering Sign-off | Stage, Marquees, structures, WA Structural, Engineering Specs, Insurances | KYRON |  | FALSE |  |  | **WORKING ITEMS
FENCING | [6 empty] | ITEM | QUANTITY | NOTES
1.8m Fence | 250m | PERTH HIRE |  | FALSE |  |  | PICNIC TABLES | 40
White Picket Fence | 300m |  |  | FALSE |  |  | ROUND CAFÉ TABLES | 30
CCB | 200m |  |  | FALSE |  |  | CAFÉ CHAIRS | 100
Bollard & Rope | 30m (stage front & large ball) |  |  | FALSE |  |  | 3m x 3m Marquee | 20
Punter Barrier | N/A |  |  | FALSE |  |  | Wine Barrels | 20
Scrim (Branded) | 200m |  |  | FALSE |  |  | Bunting | 300m
STRUCTURES | [6 empty] | Terratrak | 30pcs
Marquee (3m x 3m) | 20x Red, green and white (Carlisle) | CARLISLE / SWAN EVENTS |  | FALSE |  |  | Truss Arch (6m) | 4
Marquees (6m x 3m) | Gable facing out (MERCH tents) |  |  | FALSE |  |  | Truss Arch (4m) | 2
Scaffold centre structure | Seek quotes (Stageset / Ezy Access) |  |  | FALSE |  |  | Ballast | 2 Pallets
Stage | 9m x 7m Trailer Stage | Up Down Events |  | FALSE |  |  | White Picket Fence | 300m
|  |  |  | FALSE |  |  | 1.8m Fence | 250m
|  |  |  | FALSE |  |  | CCB | 200m
SITE & TURF MITIGATION | [6 empty] | Popcorn Machine | 1
Site Manager | See Crew Schedule |  |  | FALSE |  |  | Awnings (5m) | 2
Site Crew | See Crew Schedule |  |  | FALSE |  |  | Awnings (4m) | 3
Trakmatt | 50pcs | PERTH HIRE SHOP |  | FALSE |  |  | Trailer Stage (9m x 7m) | 1
Terratrak | 40sqm | EVENT FLOORING WA |  | FALSE |  |  | Generator (60KVA) | 2
Ballast | 2 Pallets blocks. + 12x 500kg concrete blocks |  |  | FALSE |  |  | Generator (80KVA) | 1
|  |  |  | FALSE |  |  | Generator (7KVA) | 6
PRODUCTION & AV | [6 empty] | Generator (150KVA) * Stage | 1
Production Manager | 4 Days |  |  | FALSE |  |  | Festoon
Audio |  | LUX Events / EAVP |  | FALSE |  |  | Lighting Tower | 2
Video |  | LUX Events / EAVP |  | FALSE |  |  | VMS Board | 1
Lighting |  | LUX Events / EAVP |  | FALSE |  |  | Greenery décor | 12
Production Labour |  | LUX Events / EAVP |  | FALSE |  |  | Site Office (20ft) | 1
Truss | 4x 6m(W) x 3m (H) Truss Arch 2x 4m (W) x 3m (H) Truss Arch | LUX Events / EAVP |  | FALSE |  |  | Ticket box (20ft) | 1
POWER
60kva | 2 | PERTH HIRE SHOP |  | FALSE
80kva | 2 | PERTH HIRE SHOP |  | FALSE
55kva | 1 | PERTH HIRE SHOP |  | FALSE
23kva | 1 | PERTH HIRE SHOP |  | FALSE
7kva | 4 | PERTH HIRE SHOP |  | FALSE
FALSE
WASTE | [6 empty] | Container Bar (20ft) | 1
Sulos (FOH) | Create Waste Management Plan to give to VL | Venue to provide (Quay Clean) |  | FALSE |  |  | Portaloos | 30
Cleaners |  |  |  | FALSE |  |  | ADA Portaloos | 2
CoC |  |  |  | FALSE |  |  | Coolroom | 1
660L Sulos BOH |  |  |  | FALSE |  |  | Scaffold Tower | 1 | Pumptruck & clean required after each night
|  |  |  | FALSE |  |  | 1.8m Trestles | 24
|  |  |  | FALSE |  |  | 2.4m Trestles | 20
SITE FURNITURE | [6 empty] | White Pippee chairs | 40
1.8m Trestles |  |  |  | FALSE |  |  | Checkered tablecoth | 150
2.4m Trestles |  |  |  | FALSE |  |  | Fire Extinguishers | 8
Pippee Chairs |  |  |  | FALSE |  |  | Hard Stand Forklift | 1
Picnic Tables |  |  |  | FALSE |  |  | Telehandler 2.5t Grass Terrain | 1
Round coffee tables |  |  |  | FALSE |  |  | 10d Scissor | 1
Café Chairs |  |  |  | FALSE |  |  | Trakmatt | 50pcs
THEMING / DÉCOR
Plants & Greenery |  |  |  | FALSE
Awnings |  |  |  | FALSE
Wine Barrels |  |  |  | FALSE
Bunting |  |  |  | FALSE
Checkered Tablecloths | 150x |  |  | FALSE
FALSE
SAFETY
SWMS / INSURANCES |  |  |  | FALSE
SAFETY OFFICER | 9 Days |  |  | FALSE
JSA |  |  |  | FALSE
Safety Signage, Bunting Kit |  |  |  | FALSE
EMERGENCY EVAC KIT |  |  |  | FALSE
Fire Extinguishers |  | HECS Fire & Safety |  | FALSE
MACHINERY
2.5t ALL TERRAIN FORKLIFT |  | PERTH HIRE SHOP |  | FALSE
10D SCISSOR |  | PERTH HIRE SHOP |  | FALSE
TRAY BACK UTE | KYRON |  |  | FALSE
FALSE
FALSE
FALSE
POWER
GENERATORS | Generator (60KVA) 2 Generator (80KVA) 1 Generator (7KVA) 6 Generator (150KVA) * Stage 1 |  |  | FALSE
ELECTRICIANS | Install + Form5 | LOBEL |  | FALSE
DISTRO |  | LOBEL |  | FALSE
FESTOON | 350M | LOBEL / MIKTRIK? |  | FALSE
CABLE TRAP | 50m | PERTH HIRE SHOP |  | FALSE
SITE LX | 2x Lighting Towers | PERTH HIRE SHOP |  | FALSE
SECURITY
ASSET PROTECTION | Create Asset security schedule to provide to VL |  |  | FALSE
SECURITY | Create security schedule in accordance with Liquor Licencing and Areas |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
MEDICAL
FIRST AID | FIRST AID Schedule to provide to VL |  |  | FALSE
FIRST AID POST | Confirm structure requirements for First Aid (3m x 3m or 6m x 3m) |  |  | FALSE
FALSE
FALSE
FALSE
FALSE

## POWER
POWER REQUIREMENTS
GENERATORS
KVA | QTY | NOTES /LOCATION | DELIVERY | COLLECTION
150 |  | STAGE | 2026-08-03 | 2026-08-12
60kva | 2 | S60 | 2026-08-31 | 2026-08-12
80kva | 2 | OPS COMPOUND | 2026-08-03 | 2026-08-12
55kva | 1 | VENDORS | 2026-08-03 | 2026-08-12
23kva | 1 | / | 2026-08-03 | 2026-08-12
7kva | 4 | ACTIVITIES / SPARES | 2026-08-03 | 2026-08-12
POWER DISTRO / CABLE COVER
OUTLETS | QTY REQUIRED | NOTES /LOCATION | DELIVERY | COLLECTION
63a | 1 | STAGE | 2026-08-03 | 2026-08-12
32a | 8 | Vendors BOH
15a | 1 | OPS COMPOUND | 2026-08-02 | 2026-08-12
10a | 2 | VENDORS | 2026-08-02 | 2026-08-12
| 1 | BRIDGE | 2026-08-03 | 2026-08-12
| 4 | ACTIVITIES / SPARES | 2026-08-03 | 2026-08-12
| 50 | CABLETRAP
SITE LX
ITEM | QTY | NOTES /LOCATION | DELIVERY | COLLECTION
| 1 | STAGE | 2026-08-03 | 2026-08-12
Fluros | 20 | Marquee lighting
| 1 | OPS COMPOUND | 2026-08-02 | 2026-08-12
| 2 | VENDORS | 2026-08-02 | 2026-08-12
| 1 | BRIDGE | 2026-08-03 | 2026-08-12
| 4 | ACTIVITIES / SPARES | 2026-08-03 | 2026-08-12
ELECTRICIANS / PERMITS
ITEM | QTY | NOTES /LOCATION | DELIVERY | COLLECTION
| 1 | STAGE | 2026-08-03 | 2026-08-12
100 | 0 | n/a
80 | 1 | OPS COMPOUND | 2026-08-02 | 2026-08-12
60 | 2 | VENDORS | 2026-08-02 | 2026-08-12
20 | 1 | BRIDGE | 2026-08-03 | 2026-08-12
7 | 4 | ACTIVITIES / SPARES | 2026-08-03 | 2026-08-12

## ESTIMATE
Infrastructure |  | Estimate |  | QUOTE | TOTAL | NOTES |  | OPERATIONS / LOGISTICS | SITE MANAGEMENT / CREW | KYRON
Marquees / Structures/ Furniture |  | 35000 |  | 25000 |  |  |  | MGMT DELIVERY | ONSITE DELIVERY | TOTAL
Portaloos |  | 8000 |  | 10906 | 10906 |  | 1 | 51620 | 11112 | 62732
LX / Festoon |  | 10000 |  | 10000
Portables (Site Office, Ticket Box) |  | 5000 |  | 5000 | 2000 |  | 2 | 40500 | 24085 | 64585
Fencing (White Picket, CCB) |  | 12000 |  | 8000 | 7707.5 |  |  |  |  | 6458.5 | GST
Machinery / Fuel |  | 8000 |  | 3300 | 3000 |  |  |  |  | 71043.5
Generators / Power Distro |  | 35000 |  | 25000
Theming / Décor / Signage |  | 35000 |  | 10000
Cool Rooms / Site Misc |  | 1000 |  | 4000
Turf Mitigation |  | 2000 |  | 2000
|  | 151000 | #REF! | 103206 | 47794
Operations / Logistics (inc Staffing) |  | HOURS |  | POSSIBLE REDUCE
Project Manager |  | 32500 | 32500 | 32500 | See MGMT Schedule
Operations Manager |  | 8000 | 5000 | 8000 | See MGMT Schedule
Admin/Account Manager |  |  | 6520 | 0 | See MGMT Schedule
Safety Officer (Onsite) |  |  | 7600 | 0 | Venue to provide
Site Manager |  |  | 11420.5 | 0 | See MGMT Schedule
Forklift Operater |  | 3249.5 | 1909.5 | 3249 | See Site Crew Schedule
EWP Operater |  | 1909.5 | 3249.5 | 1909 | See Site Crew Schedule
Site Crew |  | 5953 | 8340 | 7000 | See Site Crew Schedule
|  | 51612 | #REF! | 52658
Staging / AV |  | Estimate $
Stage (9m x 7m) |  | 15000 |  | 15000
Backline |  | 2500 |  | 2000
AV |  | 25000 |  | 10000 | 10000
Production Manager / Stage Manager |  | 5000 |  | 5000
Stage Manager |  | 5 |  | 0
AV Labour |  | 3000 |  | 2000
Truss Arches |  | 5000 |  | 5000
|  | 55505 | #REF! | 39000
Programming / Performers |  | $
Roving Performers |  | 15000 |  | 7500
Stage/ DJ Performers |  | 40000 |  | 20000
Face painters/ artists |  | 3500
Fireworks |  | 30000 |  | 10000
Programming |  | 10000 | 88500 | 0
Subtotal |  | 98500 | 88500 | 37500
TOTAL |  | 356617 |  | 232364
| GST | 35661.7
| TOTAL | 392278.7 |  | 255600.4

## CREW SCHEDULE
CREW SCHEDULE | [7 empty] | $ / ROLE ¦ ACTUALS
Saturday 01/08/26 |  |  |  | ROLE | $ / HR ¦ RATE | TOTAL ($) |  | SITE MANAGER ($) | SITE CREW ($) | FORK OPS ($) | EWP OPS ($)
START | FINISH | SCHEDULED HRS (Inc BREAKS) | ACTUALS |  |  |  | ONSITE | 10180.5 | 5953 | 3249.5 | 1909.5
8:00AM | 4:00PM | 5 | 7.5 | SITE MANAGER | 125 | 937.5 | PRE / POST | 1240 | 5652.5
8:00AM | 4:00PM | 5 | 7.5 | SITE CREW 1 | 69 | 517.5 |  |  | #N/A
8:00AM | 1:00p, | 5 | 7.5 | SITE CREW 2 | 69 | 517.5
7.5
[5 empty] | DAILY TOTAL ($) | 1972.5
Sunday 02/08/2026 |  | BUMP-IN | BUMP-IN |  |  |  |  | 11420.5
START | FINISH | TOTAL HRS (Inc BREAKS) | TOTAL HRS (Inc BREAKS)
[5 empty] | 125 | 0
[5 empty] | 82 | 0
[5 empty] | DAILY TOTAL ($) | 0
Monday 03/08/2026 |  | BUMP-IN | BUMP-IN
START | FINISH | TOTAL HRS (Inc BREAKS) | TOTAL HRS (Inc BREAKS)
7:00AM | 7:00PM | 11.5 | 11.5 | SITE MANAGER | 100 | 1150
7:00AM | 6:00PM | 10.5 | 10.5 | SITE CREW 1 | 56 | 588
7:00AM | 5:00PM | 9.5 | 9.5 | SITE CREW 2 | 56 | 532
7:00AM | 5:00PM | 9.5 | 9.5 | EWP OP | 67 | 636.5 |  |  |  | 3778
7:00AM | 5:00PM | 9.5 | 9.5 | FORK OP | 67 | 636.5
[5 empty] | DAILY TOTAL ($) | 3543
Tuesday 04/08/2026 |  | BUMP-IN | BUMP-IN
START | FINISH | TOTAL HRS (Inc BREAKS) | TOTAL HRS (Inc BREAKS)
7:00AM | 7:00PM | 11.5 | 11.5 | SITE MANAGER | 100 | 1150
7:00AM | 6:00PM | 10.5 | 10.5 | SITE CREW 1 | 56 | 588
7:00AM | 5:00PM | 9.5 | 9.5 | SITE CREW 2 | 56 | 532
7:00AM | 5:00PM | 9.5 | 9.5 | EWP OP | 67 | 636.5
7:00AM | 5:00PM | 9.5 | 9.5 | FORK OP | 67 | 636.5
[5 empty] | DAILY TOTAL ($) | 3543
Wednesday 05/08/2026 |  | AC MILAN VS INTER | AC MILAN VS INTER
START | FINISH | TOTAL HRS (Inc BREAKS) | TOTAL HRS (Inc BREAKS)
7:00AM | 9:30PM | 13.5 | 13.5 | SITE MANAGER | 100 | 1350
7:00AM | 7:00PM | 11.5 | 11.5 | SITE CREW 1 | 56 | 644
7:00AM | 6:00PM | 10.5 | 10.5 | SITE CREW 2 | 56 | 588
7:00AM | 6:00PM | 10.5 | 10.5 | FORKS | 67 | 703.5
10.5
5:30PM | 9:30PM | 4 | 4 | SITE OPS | 69 | 276
5:30PM | 9:30PM | 4 | 4 | SITE OPS | 69 | 276
[5 empty] | DAILY TOTAL ($) | 3837.5
Thursday 06/08/2026 |  | DOWN DAY | DOWN DAY
START | FINISH | TOTAL HRS (Inc BREAKS) | TOTAL HRS (Inc BREAKS)
9:00am | 3:00pm | 5.5 | 5.5 | SITE MANAGER | 101 | 555.5
[5 empty] | DAILY TOTAL ($) | 555.5
Friday 07/08/2026 |  | Open Training Inter & Juventus | Open Training Inter & Juventus
START | FINISH | TOTAL HRS (Inc BREAKS) | TOTAL HRS (Inc BREAKS)
7:00AM | 9:30PM | 13.5 | 13.5 | SITE MANAGER | 100 | 1350
7:00AM | 7:00PM | 10.5 | 10.5 | SITE CREW 1 | 56 | 588
7:00AM | 6:00PM | 9.5 | 9.5 | FORKS | 67 | 636.5
5:30PM | 9:30PM | 4 | 4 | SITE CREW | 69 | 276
5:30PM | 9:30PM | 4 | 4 | SITE CREW | 69 | 276
[5 empty] | DAILY TOTAL ($) | 3126.5
Saturday 08/08/2026 |  | INTER VS JUVENTUS | INTER VS JUVENTUS
START | FINISH | TOTAL HRS (Inc BREAKS) | TOTAL HRS (Inc BREAKS)
6:00AM | 5:30PM | 11 | 11 | SITE MANAGER | 100 | 1100
5:30PM | 12:00am | 6 | 6 | SITE / OPS MANAGER | 125 | 750
7:00AM | 7:00PM | 10.5 | 10.5 | SITE CREW 1 | 69 | 724.5
7:00AM | 6:00PM | 9.5 | 9.5 | SITE CREW 2 | 69 | 655.5
|  |  | 9.5 |  |  | 0
[5 empty] | DAILY TOTAL ($) | 3230
Sunday 09/08/2026 |  | AFL FOOTBALL GAME (TBC) | AFL FOOTBALL GAME (TBC)
START | FINISH | TOTAL HRS (Inc BREAKS) | TOTAL HRS (Inc BREAKS)
7:00AM | 7:00PM | 11.5 | 11.5 | SITE MANAGER | 125 | 1437.5
7:00AM | 7:00PM | 11.5 | 11.5 | SITE CREW 1 | 74 | 851
[5 empty] | DAILY TOTAL ($) | 2288.5
Monday 10/08/2026 |  | BUMP-OUT | BUMP-OUT
START | FINISH | TOTAL HRS (Inc BREAKS) | TOTAL HRS (Inc BREAKS)
7:00AM | 7:00PM | 11.5 | 11.5 | SITE MANAGER | 100 | 1150
7:00AM | 6:00PM | 10.5 | 10.5 | SITE CREW 1 | 56 | 588
7:00AM | 5:00PM | 9.5 | 9.5 | SITE CREW 2 | 56 | 532
7:00AM | 5:00PM | 9.5 | 9.5 | EWP OP | 67 | 636.5
7:00AM | 5:00PM | 9.5 | 9.5 | FORK OP | 67 | 636.5
[5 empty] | DAILY TOTAL ($) | 3543
Tuesday 11/08/2026 |  | BUMP-OUT | BUMP-OUT
START | FINISH | TOTAL HRS (Inc BREAKS) | TOTAL HRS (Inc BREAKS)
7:00AM | 7:00PM | 11.5 | 11.5 | SITE MANAGER | 100 | 1150
7:00AM | 6:00PM | 10.5 | 10.5 | SITE CREW 1 | 56 | 588
7:00AM | 5:00PM | 9.5 | 9.5 | SITE CREW 2 | 56 | 532
7:00AM | 5:00PM | 9.5 | 9.5 | FORK OP | 67 | 636.5
[5 empty] | DAILY TOTAL ($) | 2906.5
[5 empty] | TOTAL | 28546
[5 empty] | GST | 2854.6
[5 empty] | TOTAL (inc GST) | 31400.6

## MGMT SCHEDULE
OPERATIONS / LOGISTICS MGMT
1/6/2026 ¦ WEEK 1 |  | TASKS | HRS | COMPLETED | ROLE | $ / HR ¦ RATE | TOTAL ($)
|  | Weekly Team Meetings | 3 | FALSE
| 1 | Site Map Development | 10 | FALSE | Project Manager | 115
| 2 | Master Schedule | 3 | FALSE
| 3 | Scope Requirements | 3 | FALSE
| 4 | RFQ Suppliers | 3 | FALSE
| 5 | Risk Management Plan 001 | 4 | FALSE
| 6 | Insurance PPL / Vendor Insurances | 3 | FALSE
|  | TOTAL HRS (ESTIMATE) | 29 |  |  |  | 3335
8/6/2026 ¦ WEEK 2 |  | TASKS | HRS | COMPLETED | ROLE | $ / HR ¦ RATE | TOTAL ($)
|  | Weekly Team Meetings | 3 | FALSE
| 1 | Site Map Revisions | 3 | FALSE | Project Manager | 115
| 2 | Major Structures | 4 | FALSE | Project Manager
| 3 | RFQ Suppliers / Insurances | 3 | FALSE | Operations Manager
| 4 | Budget | 3 | FALSE | Admin/Accounts
| 5 | Risk Management Plan 002 | 6 | FALSE | Project Manager
| 6 | EMP 001 | 4 | FALSE | Project Manager
|  | TOTAL HRS (ESTIMATE) | 26 |  |  |  | 2990
15/6/2026 ¦ WEEK 3 |  | TASKS | HRS | COMPLETED | ROLE | $ / HR ¦ RATE | TOTAL ($)
|  | Weekly Team Meetings | 3 | FALSE
| 1 | Site Map (Revs) | 1 | FALSE | Project Manager | 115
| 2 | Master Schedule Updates | 3 | FALSE
| 3 | Transport Schedule | 3 | FALSE
| 4 | Book Infrastructure Suppliers | 3 | FALSE
| 5 | Risk Management Plan 003 ¦ For Review | 3 | TRUE
| 6 | Staging / AV Suppliers | 3 | FALSE
|  | TOTAL HRS (ESTIMATE) | 22 |  |  |  | 2530
22/6/2026 ¦ WEEK 4 |  | TASKS | HRS | COMPLETED | ROLE | $ / HR ¦ RATE | TOTAL ($)
|  | Weekly Team Meetings | 3 | FALSE
| 1 | Site Map Development | 3 | FALSE | Project Manager | 115
| 2 | Master Schedule | 3 | FALSE
| 3 | Scope Requirements | 3 | FALSE
| 4 | Security / Asset Protection | 3 | FALSE
| 5 | Crew Scheduling / Confirmations | 4 | FALSE
| 6 | Budget / Review / Final Sign-off | 3 | FALSE
|  | TOTAL HRS (ESTIMATE) | 22 |  |  |  | 2530
29/6/2026 ¦ WEEK 5 |  | TASKS | HRS | COMPLETED | ROLE | $ / HR ¦ RATE | TOTAL ($)
|  | Weekly Team Meetings | 3 | FALSE
| 1 | Site Map Development | 2 | FALSE | Project Manager | 115
| 2 | Master Schedule Confirmation / Sign-off | 4 | FALSE | Project Manager | 115
| 3 | Transport / Logistics Schedule | 3 | FALSE | Ops Manager
| 4 | Confirm Suppliers / Budget Sign-off | 4 | FALSE
| 5 | Staffing Schedule confirmed | 4 | FALSE
| 6 |  | 4 | FALSE
| 7 | General Misc / SWMS docs | 3 | FALSE
|  | TOTAL HRS (ESTIMATE) | 22 |  |  |  | 2530
05/7/2026 ¦ WEEK 1 |  | TASKS | HRS | COMPLETED | ROLE | $ / HR ¦ RATE | TOTAL ($)
|  | Weekly Team Meetings | 3 | FALSE
| 1 | Scheduling Vendors/Contractors | 3 | FALSE | Project Manager | 115
| 2 | Master Schedule Updates | 3 | FALSE
| 3 | Budget / Review Final | 3 | FALSE | Admin/Accounts (1.5hrs) PM (1.5hrs)
| 4 | First Aid / Medical Sign-off | 3 | FALSE
| 5 | Waste Management | 4 | FALSE
| 6 | General Misc | 3 | FALSE
|  | TOTAL HRS (ESTIMATE) | 22 |  |  |  | 2530
12/7/2026 ¦ WEEK 1 |  | TASKS | HRS | COMPLETED | ROLE | $ / HR ¦ RATE | TOTAL ($)
|  | Weekly Team Meetings | 3 | FALSE
| 1 | Scheduling Vendors/Contractors | 3 | FALSE | Project Manager | 115
| 2 | Master Schedule Updates | 3 | FALSE
| 3 | Budget / Review Final | 3 | FALSE | Admin/Accounts (1.5hrs) PM (1.5hrs)
| 4 | First Aid / Medical Sign-off | 3 | FALSE
| 5 | Waste Management | 4 | FALSE
| 6 | General Misc | 3 | FALSE
|  | TOTAL HRS (ESTIMATE) | 22 |  |  |  | 2530
19/7/2026 ¦ WEEK 1 |  | TASKS | HRS | COMPLETED | ROLE | $ / HR ¦ RATE | TOTAL ($)
|  | Weekly Team Meetings | 3 | FALSE
| 1 | Scheduling Vendors/Contractors | 3 | FALSE | Project Manager | 115
| 2 | Master Schedule Updates | 3 | FALSE
| 3 | Budget / Review Final | 3 | FALSE | Admin/Accounts (1.5hrs) PM (1.5hrs)
| 4 | First Aid / Medical Sign-off | 3 | FALSE
| 5 | Waste Management | 4 | FALSE
| 6 | General Misc | 3 | FALSE
|  | TOTAL HRS (ESTIMATE) | 22 |  |  |  | 2530
26/7/2026 ¦ WEEK 1 |  | TASKS | HRS | COMPLETED | ROLE | $ / HR ¦ RATE | TOTAL ($)
|  | Weekly Team Meetings | 3 | FALSE
| 1 | Scheduling Vendors/Contractors | 3 | FALSE | Project Manager | 115
| 2 | Master Schedule Updates | 3 | FALSE
| 3 | Budget / Review Final | 3 | FALSE | Admin/Accounts (1.5hrs) PM (1.5hrs)
| 4 | First Aid / Medical Sign-off | 3 | FALSE
| 5 | Waste Management | 4 | FALSE
| 6 | General Misc | 3 | FALSE
|  | TOTAL HRS (ESTIMATE) | 22 |  |  |  | 2530
01/8/2026 ¦ WEEK 1 |  | TASKS | HRS | COMPLETED | ROLE | $ / HR ¦ RATE | TOTAL ($)
|  | Weekly Team Meetings | 3 | FALSE
| 1 | Scheduling Vendors/Contractors | 3 | FALSE | Project Manager | 115
| 2 | Master Schedule Updates | 3 | FALSE
| 3 | Budget / Review Final | 3 | FALSE | Admin/Accounts (1.5hrs) PM (1.5hrs)
| 4 | First Aid / Medical Sign-off | 3 | FALSE
| 5 | Waste Management | 4 | FALSE
| 6 | General Misc | 3 | FALSE
|  | TOTAL HRS (ESTIMATE) | 22 |  |  |  | 2530

## BUDGET
EXPENDITURE BUDGET
APPROVER: | [5 empty] | RESPONSIBLE: KYRON PTY LTD
ITEM | SUPPLIER | INSURANCE | QUOTED ($) ex gst | ACTUAL ($) inc GST | QUOTE (link) | APPROVED | PAID | NOTES | RFQ # | RFQ REGISTER
POWER / ELECTRICIANS
GENERATORS 2x 80kva 2x 60kva 2x 55kva 1x 23kva 4x 7kva) | PERTH HIRE SHOP |  | 7360 | [5 empty] | RFQ-001 | QUOTE 1 | TOILETS
Generator Transport | PERTH HIRE SHOP |  | 2160
POWER DISTRO | LOBEL | [7 empty] | PERTH HIRE SHOP
ELECTRICIANS / LABOUR | LOBEL | [8 empty] | ITEM(S) | 40x Portaloos
FORM 5 SIGN-OFF | LOBEL | [9 empty] | 2x ADA Portaloos
LX TOWER | PERTH HIRE SHOP |  | 650
SITE LX ¦ FESTOON | TBC
TOTAL |  |  | 10170 | 0 | [5 empty] | DELIVERY | Delivery
PORTABLES | [9 empty] | COLLECTION | 2026-08-03
20ft Site Office | KYRON |  | 350 | [6 empty] | LOCATION | 2026-08-11
20ft Box Office | [10 empty] | OPTUS STADIUM
20ft Container Bar | [8 empty] | RFQ-002 | QUOTE 2
Transport | PHS | [8 empty] | ITEMS | MACHINERY / TRAKMATT
PERTH HIRE SHOP
TOTAL |  |  | 350 | 0 | [6 empty] | 2.5t Hardstand Forklift
TOILETS | [10 empty] | 2.5t Telehandler (Grass terrain tyres)
30x Portaloos | PERTH HIRE SHOP |  | 2550 |  | QUOTE | [5 empty] | 10D Scissor
2x ADA Portaloos | PERTH HIRE SHOP |  | 316 | [6 empty] | DELIVERY | Trakmatt (50pcs)
Transport | PERTH HIRE SHOP |  | 650 | [6 empty] | COLLECTION | 2026-08-01
Weekend Callout | PERTH HIRE SHOP |  | 350
Toilet servicing / pump-out (4) | PERTH HIRE SHOP |  | 7040 | [6 empty] | LOCATION | 2026-08-11
OPTUS STADIUM
TOTAL |  |  | 10906 | 0 |  |  |  |  | RFQ-003 | QUOTE 3
STAGING / AV | [9 empty] | ITEMS | FENCING / WHITE PICKET / CCB
Stage (9m x 7m) Trailer Stage | [10 empty] | CBWA
Audio | [10 empty] | 2.5t Hardstand Forklift
Lighting | [10 empty] | 2.5t Telehandler (Grass terrain tyres)
10D Scissor
[10 empty] | DELIVERY | Trakmatt (50pcs)
TOTAL |  |  | 0 | 0 | [5 empty] | COLLECTION | 2026-08-01
MARQUEES / STRUCTURES | [9 empty] | LOCATION | 2026-08-11
OPTUS STADIUM
[9 empty] | RFQ-003 | QUOTE 3
[10 empty] | ITEMS | MARQUEES
CBWA
18x (3m x 3m) Red/green/white marquees
TOTAL |  |  | 0 | 0 | [6 empty] | 2x (6m x 3m) Hoeker P-Series Structure
FENCING | [10 empty] | 2x (12m x 3m) Hoeker
1.8m Fence (INSTALLED) - Inc 3 gates - 2 double 1 single - Inc bracing every 1panel with extra weight for wind rating up to 100km/h - Inc 1x pallet of white blocks (feet) | PERTH HIRE SHOP |  | 3087.5 | [6 empty] | DELIVERY
CCB | PERTH HIRE SHOP |  | 540 | [6 empty] | COLLECTION | 2026-08-01
Transport | PERTH HIRE SHOP |  | 380 | [6 empty] | LOCATION | 2026-08-11
White Picket | CBWA |  | 3500
Transport | CBWA |  | 200 | [7 empty] | OPTUS STADIUM
TOTAL |  |  | 7707.5 | 0
MACHINERY
3t Rough Terrain Forklift (weekly hire) | PERTH HIRE SHOP |  | 1400
8.1m Scissor Lift Rough Terrain 2755RT 4x4 27ft | PERTH HIRE SHOP |  | 500
Transport | PERTH HIRE SHOP |  | 800
Deisel ¦ 100l @ $3.00/l | KYRON |  | 300
TOTAL |  |  | 3000 | 0
OPERATIONS (inc Staff)
TOTAL |  |  | 0 | 0
SITE & TURF MITIGATION
Trakmatt (50x) | PERTH HIRE SHOP |  | 900
Terratrak |  |  | 1200
TOTAL |  |  | 2100 | 0
FURNITURE (SITE / PATRON)
TOTAL |  |  | 0 | 0
THEMING / DÉCOR
TOTAL |  |  | 0 | 0
MISCELANEOUS
VMS Board |  | PERTH HIRE SHOP | 200
TOTAL |  |  | 200 | 0
SITE TOTAL |  |  | 34433.5 | 0

## TOPLINE SCHEDULE
TIME | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
| Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
| 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13
SITE MANAGER ONSITE
| SITE MARK OUT |  |  |  | EVENT OPS TEAM ONSITE
| 8:00am |  |  |  | 7:00am
FESTIVAL COMMENCES
3:30pm
AC MILAN V INTER
Gates: 5.30pm
KO: 7.00pm

## MASTER SCHEDULE
CALCIO ITALIANO 2026 Little Italy Festival
BUILD SCHEDULE
Saturday 1st August 2026 - Tuesday 12th August 2026
2026-08-01
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES | COMPLETED
700 | 2pm | ON-SITE | KYRON | PM/ Site Manager Onsite (Markout stage/site infrastructure) |  | PERSON 1 |  | FALSE
7am | 8:30 | COLLECTION | KYRON | Pack Site Tool Chest at Warehouse > Deliver to Site |  |  |  | FALSE
700 | 1300 | COLLECTION | TBC | Safety Officer Onsite |  |  |  | FALSE
700 | 1pm | ON-SITE | KYRON | 2x Site Crew onsite |  |  |  | FALSE
0.29167 | 8:30 | ON-SITE | PERTH HIRE SHOP | 50x trakmatt |  |  | ON-SITE | FALSE | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry)
8am | 10am | DELIVERY | EVENT FLOORING WA | 40x Terratrak |  |  |  | FALSE
8am | 10am | DELIVERY | PERTH HIRE SHOP | 10D Scissor, 3t AT Fork in compound |  |  |  | FALSE
0.29167 | 10am | DELIVERY | KYRON | Site Water Delivered |  |  |  | FALSE
0.29167 | 1pm | INSTALL | FENCED / KYRON | Build Ops Compound fenceline (Scrim) ¦ Crane pl or lawn |  |  |  | FALSE
9:00am | 1pm | DELIVERY | KYRON | Chocks / 20x 4ft trestles delivered |  |  |  | FALSE
9:00am | 1pm | DELIVERY | KYRON | Set up site office / Ops compound |  |  |  | FALSE
9:00am | 1pm | INSTALL | PERTH HIRE SHOP | Generators ¦ 1x 60kva |  |  |  | FALSE
1700 | 700 | SECURITY | KYRON | Secure Ops Compound |  |  |  | FALSE
2026-08-02
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
0.29167 | 0.72917 | COLLECTION | KYRON |  |  |  |  | FALSE
1800 | 700 | COLLECTION | [5 empty] | FALSE
2026-08-03
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES |  | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry)
0.29167 | 5pm | ON-SITE | KYRON |  |  |  |  | FALSE
0.29167 | 0.72917 | ON-SITE | KYRON |  |  |  |  | FALSE
0.29167 | 0.72917 | ON-SITE |  |  |  |  | ON-SITE | FALSE
0.29167 | 0.72917 | ON-SITE | [5 empty] | FALSE
0.29167 | 0.72917 | INSTALL | [5 empty] | FALSE
700 | 1730 | ON-SITE | [5 empty] | FALSE
1800 | 700 | SECURITY | VL | Compound Secured overnight |  |  |  | FALSE
2026-08-04
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
0.29167 |  | ON-SITE | KYRON
[9 empty] | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry)
1800 | 700 | SECURITY | VL | Compound Secured overnight
2026-08-05 |  |  | EVENT DAY 1
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
0.29167 |  | ON-SITE | KYRON |  |  |  |  | FALSE
|  |  | KYRON | 3x Site Crew onsite |  |  |  | FALSE
0.29167 |  | INSTALL | [5 empty] | FALSE
0.29167 |  | ON-SITE |  |  |  |  | ON-SITE | FALSE
0.29167 |  | INSTALL | [5 empty] | FALSE
0.29167 |  | COLLECTION | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE
|  | DELIVERY | [5 empty] | FALSE
|  | DELIVERY | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry)
|  | DELIVERY | [5 empty] | FALSE
|  | DELIVERY | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE
|  | DELIVERY | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE
1200 | 1400 | DELIVERY | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE
1800 | 700 | SECURITY | VL | Compound Secured overnight |  |  |  | FALSE
2026-08-06 |  |  | EVENT DAY 2
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
|  | ON-SITE | KYRON |  |  |  |  | FALSE
|  | ON-SITE | [5 empty] | FALSE
|  | ON-SITE |  |  |  |  | ON-SITE | FALSE
700 | 1700 | INSTALL | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE
|  | DELIVERY | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE
|  | DELIVERY | [5 empty] | FALSE
|  | ON-SITE | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry)
|  | DELIVERY | [5 empty] | FALSE
|  | ON-SITE | [5 empty] | FALSE
1800 | 700 | SECURITY | ACE SECURITY | Compound Secured overnight |  |  |  | FALSE
2026-08-07 |  |  | SHOWDAY
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
0.29167 |  | COLLECTION | KYRON |  |  |  |  | FALSE
0.29167 |  | ON-SITE | [5 empty] | FALSE
0.29167 |  | ON-SITE |  |  |  |  | ON-SITE | FALSE
0.375 |  | ON-SITE | [5 empty] | FALSE
FALSE
0.29167 |  | INSTALL | [5 empty] | FALSE
0.29167 |  | ON-SITE | [5 empty] | FALSE
0.54167 |  | ON-SITE | [5 empty] | FALSE
7:00 |  | INSTALL | [5 empty] | FALSE
0.41667 |  | ON-SITE | [5 empty] | FALSE
|  | SHOW TIME | [5 empty] | FALSE | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry) | ON-SITE | ESM | Traffic control onsite (Camfield dr site entry)
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
0.9375 | [7 empty] | FALSE
|  | BUMP OUT | [5 empty] | FALSE
|  | BUMP OUT | [5 empty] | FALSE
22:30 | 1:00 | INSTALL | [5 empty] | FALSE
1800 | 700 | SECURITY | Venueslive | Asset secuirty overnight |  |  |  | FALSE
2026-08-08
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
|  | ON-SITE | KYRON |  |  |  |  | FALSE
FALSE
|  | COLLECTION | [5 empty] | FALSE
|  | BUMP OUT | [5 empty] | FALSE
|  | COLLECTION | [5 empty] | FALSE
|  | ON-SITE | [5 empty] | FALSE
|  | ON-SITE | [5 empty] | FALSE
|  | ON-SITE | [5 empty] | FALSE
1800 | 700 | SECURITY | Venueslive | Asset Security |  |  |  | FALSE
2026-08-09
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
|  | ON-SITE | KYRON | Site Manager Onsite (Markout stage/site infrastructure) |  |  |  | FALSE
|  | ON-SITE | [5 empty] | FALSE
|  | INSTALL | [5 empty] | FALSE
|  | ON-SITE | [5 empty] | FALSE
2026-08-10
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
2026-08-11
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
2026-08-12
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
2026-08-13
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES
FALSE
FALSE
FALSE
FALSE
2026-08-14
START | FINISH | TYPE | SUPPLIER | ACTION | LOCATION | SITE POINT OF CONTACT | NOTES

## PRODUCTION SCHEDULE
PRODUCTION SCHEDULE
2023-01-01 |  | ACTIVITY | NOTES
START | FINISH
2023-01-02 |  | ACTIVITY | NOTES
START | FINISH
2023-01-03 |  | ACTIVITY | NOTES
START | FINISH
2023-01-04 |  | ACTIVITY | NOTES
START | FINISH
2023-01-05 |  | ACTIVITY | NOTES
START | FINISH
2023-01-06 |  | ACTIVITY | NOTES
START | FINISH

## TRANSPORT SCHEDULE
TRANSPORT SCHEDULE
IN-COMING
DATE | TIME | ITEM | FROM | TRUCK TYPE | DOORS FACING | GATE ENTRY | CONTACT PERSON
2023-02-06
OUT-GOING
DATE | TIME | ITEM | FROM | TRUCK TYPE | DOORS FACING | GATE ENTRY | CONTACT PERSON

## MAJOR STRUCTURES
MAJOR STRUCTURES - CALSIO ITALIANO 2026
MARQUEES |  | MARQUEE NAME | SIZE |  | PEGGED | WEIGHTED | LIGHTING | WALLS | NOTES | DOCS RECIEVED | LINK | ENGINEER SIGN-OFF
RESPONSIBLE | TYPE |  | LENGTH | WIDTH
KYRON | ROBIAN | VENDORS | 3m | 3m | FALSE | TRUE | TRUE | ALL WALLS | 6x Green, 6x Red, 6x White | FALSE |  | FALSE
KYRON | HOKKER | PASTA | 5m | 5m | FALSE | TRUE | TRUE | ALL WALLS |  | FALSE |  | FALSE
KYRON | HOKKER | MERCH (BRIDGE) | 12m | 3m | FALSE | TRUE | TRUE | ALL WALLS |  | FALSE |  | FALSE
[5 empty] | FALSE | FALSE | FALSE |  |  | FALSE |  | FALSE
[5 empty] | FALSE | FALSE | FALSE |  |  | FALSE |  | FALSE
[5 empty] | FALSE | FALSE | FALSE |  |  | FALSE |  | FALSE
OTHER |  | STRUCTURE NAME | SIZE |  | PEGGED | WEIGHTED | NOTES |  |  | DOCS RECIEVED | LINK | ENGINEER SIGN-OFF
RESPONSIBLE | TYPE |  | LENGTH | WIDTH
[5 empty] | FALSE | FALSE |  |  |  | FALSE |  | FALSE
[5 empty] | FALSE | FALSE |  |  |  | FALSE |  | FALSE
[5 empty] | FALSE | FALSE |  |  |  | FALSE |  | FALSE
[5 empty] | FALSE | FALSE |  |  |  | FALSE |  | FALSE
[5 empty] | FALSE | FALSE |  |  |  | FALSE |  | FALSE
[5 empty] | FALSE | FALSE |  |  |  | FALSE |  | FALSE

## FENCING
FENCING
1.8M TEMPORARY FENCING
LOCATION | TYPE | LENGTH (M) | MITIGATION | TOTAL | NOTES
OPS COMPOUND | INSTALL | 55 | 5.5 | 60.5
STAGE BOH | INSTALL | 70 | 7 | 77
BAR BOH | INSTALL | 70 | 7 | 77
SOUTH OVAL / CAMFIELD | INSTALL | 30 | 3 | 33
DOUBLE GATES / WHEELS | INSTALL | 3 | 0.3 | 3.3
|  |  | 0 | 0 | 250.8
CCB (CROWD CONTROL BARRIER)
LOCATION | TYPE | LENGTH | MITIGATION | TOTAL | NOTES
150 |  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
PUNTER BARRIER
LOCATION | TYPE | LENGTH | MITIGATION | TOTAL | NOTES
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
WHITE PICKET
LOCATION | TYPE | LENGTH | MITIGATION | TOTAL | NOTES
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0

## FURNITURE DISTRO
FURNITURE DISTRO
LOCATION | CHAIRS | TABLES |  | COUCH | FRIDGE | ICE TUB | FANS | BUBBLER | LINEN | COAT RACK | MIRROR
|  | 1.8M | 2.4M
SPARE
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SUPPLIER

## TOILET RATIO CALC
TOILET RATIO CALCULATOR
GENERAL AREA |  |  | VIP AREA |  |  | SET RATIO
TYPE | QUANTITY | PANS | TYPE | QUANTITY | PANS | RATIO
16 PAN BLOCK | 0 | 0 | 16 PAN BLOCK | 0 | 0
URINAL BLOCK | 0 | 0 | URINAL BLOCK | 0 | 0
SINGLE CHEM | 40 | 40 | SINGLE CHEM | 0 | 0
ACROD | 2 | 2 | ACROD | 0 | 0
TOTAL PANS |  | 42 | TOTAL PANS |  | 0
CAPACITY |  | 3000 | CAPACITY |  | 0
75 | TOILET RATIO | 71.4286 | 45 | TOILET RATIO | #DIV/0!

## SITE MAP
SITE MAP
VERSION | LINK

## Criteria
KYLE BAILEY (KB)
FRED (PHS)
FRANK M (FM)
WENDY (VL)
TYLER (TWA)
MIZZICA
ON-SITE
INSTALL
COLLECTION
DELIVERY
SHOW TIME
ON-SITE
BUMP OUT
DROP OFF
PICK UP
SECURITY
A
B
C
D
E
F
G
H
I
J
K
L
M
N
O
P
Q
ROBIAN
HOKKER
FLAT BED
HIAB
TILT TRAY
SIDELOADER
CAB
REAR
PASSENGER
DRIVER
DRY HIRE
INSTALL